## Sheet1
work task | week1 | week2 |  | week3 | week4 |  | week 5 | week6 | week7 | week8 |  | week9 | week10 | week11 | week12 |  | week13 | week14 | wwek15 |  | week 16 | week 17 |  | week18 | week 19
1.1 Initiation
1.1.1 Define project Scope
1.1.2 StakeHolder Aanlysis |  |  | ♦
1.1.3 Approvals & Charter Preparation
1.2 Planning
1.2.1 Develop project Plane and Schedule
1.2.2 Risk Assessment
1.2.3 Resource allocation
1.3 Monitioring & Control
1.3.1 Progress Tracking
1.3.2 Issue Managment
1.3.3 Quality assurance
1.4 Closure
1.4.1 FInal review & Report
1.4.2 Documentation and Handover | [5 empty] | ♦
2 System Analysis & Design
2.1 Requirement Gathering
2.1.1 Collect Academic Requirments
2.1.2 COllect Administrative Requirment
2.1.3 Collect Personal/Student support Requirements
2.2 Software Requirments Specification(SRS)
2.2.1 Functional Requirments
2.2.2 Non-Functional Requirments
2.2.3 Constraints & assumptions
2.2.4 Approval & Baseline
2.3.System Modeling
2.3.1 Develop Use Case Diagram
2.3.2 Develop Class Diagram
2.3.3. Develop Sequemc Diagram | [10 empty] | ♦
2.4 System Design
2.4.1 System Architecture
2.4.2 Database Design
2.4.3 User Interface
2.4.4 Security FrameWork
3 Core System Development
3.1 Useer Management Modeul
3.1.1 Login & Authentication
3.1.2 Role-Basaed Dashboard
3.2 Courae Registration Syatem
3.2.1 CGPA & Demand Based slot allocation
3.2.2 Course enrollment & Drop system
3.2.3 Registration conflict resolution
3.2.4 Reporting & analytic
3.3 Lost & Found
3.3.1 Item submission form
3.3.2 Verification& claim Workflow
3.3.3 Notification system
3.4 smart Location
3.4.1 Campus integration
3.4.2 AR navigation
3.4.3 Accessibility routes for disabled Studnets
3.5 Events & Notice
3.5.1 Event creation Module
3.5.2 NoticeBoard integration
3.5.3 Calendar View for students
3.6 Gymanausium Registration & payment
3.6.1 Membership Managment
3.6.2 payment gateway
3.6.3 Attendence & usage tracking
3.7 Anonymous Complaint System
3.7.1 secure submission portal
3.7.2 Complaint Categorization
3.7.3 Admin resolution Dashboard
3.8 COurse Book Referennce & Online Resources
3.8.2 Course wise book reposritory
3.9 GLobal printing system
3.10 Faculty Info
3.11 Aiub FIle share
3.12 Class Routin upcoming Events
Integration & Testing
4.1 System Integratrion | [15 empty] | ♦
4.1.1 Database Integration
4.1.2 API Connection
4.2 Testing
4.2.1 Unit Testing
4.2.2 Regression testing | [19 empty] | ♦
4.2.3 WHITE BOX
4.2.4 Black box testing
4.2.6 User Acceptance
5 Deployment and Traning
5.1 Deployment | [20 empty] | ♦
5.1.1 cloud Server setup
5.1.2 Data migration
5.1.3 Go Live
5.2 training & support
5.2.1 User Manulasa | [22 empty] | ♦
5.2.2 Helpdesk
Maintenance & Continuous ImproveMent
6.1 Monitoring
6.1.1 System health Moniotoring
6.1.2 Feedback
6.2.1 Bug FIxes
6.2.2 Feature Upgrades
6.2.3 Socalability Improvemet